## Sheet1
Timber Sale Checklist
| Consult. | Logger | Owner
A. Initial Assessment
1. Clarify landowner goals, Moratorium issues, Forest Stewardship Plan
- Certification, Forest Stewardship Plan
- Building moratorium issues
2. Hire consultant and sign contract: % or hourly
3. ID and Assess stands
- Stand conditions: ready for harvest? need thinning? timing?
- Soils & slope: wet season logging possible?
- Riparian: type out streams and wetlands, channel migration zones
- Other restricted sites: unstable slopes, special habitats, OG trees, views, etc
- Other FPA, county, or certification requirements
- Road access, landings, logging systems
4. Revenue estimate
- Estimate volume and removal by grades (sorts)
- Ballpark logging and haul costs
- ID possible log markets: prices by species and grade (price sheets)
5. Decide to move ahead with project or wait
- Stand conditions, markets, financial needs
B. Silvicultural and Harvest Design
1. Determine silvicultural and operational approach
- Thin, Regen, or mix?: Trees and dead wood to leave? Carbon considerations
- Scaled sale vs. lump sum; Cut and leave tree designation approach
- Logging system, road access needs, landings
- Riparian buffer widths and approach (Alt plan, FREP, etc)
2. Layout
- Locate & flag property boundary as necessary
- Layout timber sale boundaries, riparian buffers, and other no-entry areas
- Mark cut or leave trees, retention areas, etc as needed
3. Quantify volume to be removed & estimate net revenue
- Full grade cruise or "estimate" approach
- Refine revenue estimate: logging costs & log prices
4. Prepare & submit DNR or county permit, R-map, DNR site visit
Notes
| Consult. | Logger | Owner
C. Operational Preparation
1. Write operational prescription and bid prospectus
2. Solicit bids from logging contractors
- Payment method: splits, %, mbf vs. tons, lump sum
- Log marketing: logger or landowner? Purchase agreements with mills
- Equipment types, logging system: long vs short logs
- Trucking: self-loader, mule train, pup-trailer
3. Select logger
4. Create and sign contract between logger & landowner
- Insurance amounts & naming on policies
- Research log prices, decide on markets and sorts (pulp/firewood)
- Write cutting guidelines: bucking and sorting instructions + operational Rx
5. Send in DNR operator transfer form
| Consult. | Logger | Owner
D. Managing Operation
1. Pre-operation walk through with operator(s) and landowner
- Review contract and operational prescription
- Finalize layout with logger: road access, landings, yarding corridors, etc.
2. Supervise logging operation
- Value maximizations: splits, bucking and sorting accuracy
- Oversee loading of trucks & issue load tickets
- Damage: residual stand, soils, sensitive sites, roads, etc: suspension?
- Wet weather suspension
3. Review and cross check scale and load reports from mills
4. Final walk through: ensure clean-up happens as planned
E. Accounting
1. Total up volume and revenue numbers: final accounting report
2. Settle up with consultant and logging contractor
3. DNR and Income taxes
F. Follow-up projects
1. Prepare planting plan and order trees
2. Plant trees as requested by landowner
3. Follow-up shrub and invasive species control as needed
Notes